## Agenda
Noted! stand-up, Wed Oct 14, 2026 (Sprint 1, day 9 of 16)
Yellow cells are for notes during the meeting.
# | Topic | Minutes | Points to cover | Notes / decision
1 | Wins | 1 | Foundation (E-01) done: app skeleton, models, test setup, base layout, requirements.txt all on main. music21 half of the rendering spike done (NTT-45). Sprint 1: 20 of 65 hours done.
2 | Round robin | 8 | Each person, 1-2 min: what I did, what's next, what's blocking me. See the Team Status tab.
3 | Blockers | 3 | Daniel's Flask-Login (NTT-30): blocks login tests, logged-in fixture, 'logs you in' register test, every page needing a user. Get an ETA. Beijia's register route (NTT-27/28): Ryan's 13 tests wait on it. Route requirements are in the comment on NTT-27.
4 | Spike decision | 2 | music21 results: LilyPond failed to install, MuseScore 9 s per render, Verovio 5 s install / 0.7 s render. NTT-46 (hand-drawn SVG) now assigned to Varuzhan; confirm with Beijia. Decide by Friday so NTT-43 can build on music21 + Verovio.
5 | Sprint risk | 3 | 45 hours left, 7 days to go. Sprint ends Oct 21; Part B due Oct 22. US-04 (18 hrs) not started; depends on US-03, which depends on login. Keep everything, or finish US-01 to US-03 and move part of US-04 to Sprint 2? Check-in Friday Oct 16: if login and register route are merged, keep everything; if not, move US-04 UI and converter tasks to Sprint 2.
6 | Housekeeping | 1 | Everyone: pip install -r requirements.txt after pulling. NTT-29 is marked Done but its tests can't run until the register route exists: reopen, or close once they pass. Reviewers: review within a day.
| Total | 18

## Team Status
Person | Hours left | Open work | Waiting on | What I did | What's next | Blockers
Beijia | 14 | Register: form in review, route and hashing in progress (NTT-26 to 28). Then login tests (NTT-34), music21 converter (NTT-43, 44) | Flask-Login (NTT-30) for login tests
Daniel | 11 | Not started: login (NTT-30 to 33), new composition (NTT-35, 36)
Varuzhan | 10 | Spike: SVG prototype and write-up (NTT-46, 47), editor page (NTT-37), note-entry palette (NTT-40) | Base layout merged; NTT-37 needs Daniel's create route
Yalei | 6 | Note storage and add-note route (NTT-39, 41), logged-in fixture (NTT-111) | Login (NTT-30/31) for NTT-111
Ryan | 4 | New-composition tests (NTT-38), range validation (NTT-42) | Create route (NTT-36) for NTT-38
Total | 45

## Tasks
Key | Story | Task | Owner | Hours | Status
NTT-2 | E-01 | Set up GitHub repo, Jira board, README | Varuzhan | 2 | Done
NTT-22 | E-01 | Flask app factory, config, blueprints | Daniel | 3 | Done
NTT-23 | E-01 | SQLAlchemy models and init-db | Yalei | 5 | Done
NTT-24 | E-01 | pytest setup and fixtures | Yalei | 2 | Done
NTT-25 | E-01 | Base Jinja layout: nav, flash messages, CSS | Varuzhan | 3 | Done
NTT-26 | US-01 | Registration form template | Beijia | 2 | In Review
NTT-27 | US-01 | Register route with validation | Beijia | 2 | In Progress
NTT-28 | US-01 | Hash passwords and save the user | Beijia | 1 | In Progress
NTT-29 | US-01 | Register tests | Ryan | 3 | Done
NTT-30 | US-02 | Flask-Login and user loader | Daniel | 2 | To Do
NTT-31 | US-02 | Login form and route | Daniel | 2 | To Do
NTT-32 | US-02 | Logout route, nav changes when logged in | Daniel | 1 | To Do
NTT-33 | US-02 | @login_required on composition/library routes | Daniel | 1 | To Do
NTT-34 | US-02 | Login tests | Beijia | 3 | To Do
NTT-111 | US-02 | logged_in_client test fixture | Yalei | 1 | To Do
NTT-35 | US-03 | New-composition form | Daniel | 3 | To Do
NTT-36 | US-03 | Create route, owner = current user | Daniel | 2 | To Do
NTT-37 | US-03 | Composition editor page shell | Varuzhan | 3 | To Do
NTT-38 | US-03 | New-composition tests | Ryan | 2 | To Do
NTT-39 | US-04 | Note ordering and storage logic | Yalei | 3 | To Do
NTT-40 | US-04 | Note-entry palette UI | Varuzhan | 5 | To Do
NTT-41 | US-04 | Add-note route | Yalei | 2 | To Do
NTT-42 | US-04 | Treble-clef range validation (A3-C6) | Ryan | 2 | To Do
NTT-43 | US-04 | Composition to music21 Stream service | Beijia | 3 | To Do
NTT-44 | US-04 | Add-note tests | Beijia | 3 | To Do
NTT-45 | SP-01 | Try music21 renderers | Varuzhan | 2 | Done
NTT-46 | SP-01 | Hand-drawn SVG staff prototype | Varuzhan | 1 | To Do
NTT-47 | SP-01 | Write up the decision | Varuzhan | 1 | In Progress
|  |  | Total hours | 65
|  |  | Done | 20
|  |  | Left | 45
|  |  | % done | 30.77%
Source: Jira NTT board, Sprint 1, as of Oct 14, 2026. Hours are the story point estimates.

## Action Items
Action | Owner | Due | Done?
Example: Share Flask-Login ETA in the team chat | Daniel | Oct 15 | No